## Sheet1
| May 27, 2022 | 2003-06-01 | 2010-06-01 | 2017-06-01 | 2024-06-01 | 2001-07-01 | 2008-07-01 | 2015-07-01 | 2022-07-01 | 2029-07-01
|  | week 1 | week 2 | week 3 | week 4 | week 5 | week 6 | week 7 | week 8 | week 9
1 | Conceptualization
1.1 | Brainstorming | bar: week 1 to week 3
1.2 | Problem Formulation | bar: week 3 to week 4
2 | Project Planning
2.1 | Distribution of Work | bar: week 5
2.1 | Communication Platform | bar: week 5
2.1 | Program Structure | bar: week 5
3 | Program Creation
3.1 | Program Structure Foundation | bar: week 6
3.2 | Main Algorithm | bar: week 7
3.2 | Website Frontend | bar: week 7
3.2 | Initial Testing | bar: week 8
3.2 | Initial Debug | bar: week 8
3.2 | Final Testings | bar: week 9
3.2 | Final Debug | bar: week 9
4 | Documentation | bar: week 6 to week 9
5 | Final Presentation | bar: week 9